## Slide 1: Fezziwig PROGRAM
IT stream Managers Weekly report | UI stream
BP2S Data Technology Office
Confidential - For internal use only

## Slide 2: Agenda – UI Stream
Overall Status
Scope & Effort
Resources & Capacity
Scope Breakdown
Timeline
Epics Dashboard
Features Dashboard
Productivity
Risk & Issues
Deployments

## Slide 3: UI STREAM - Overall status
Next Milestones and Delivery | Target Date | Status
Deployment of next drop increment in IST | TBD | WIP
Completion of epic: Effective Dating OW / UW – Security Mastering | TBD | WIP
L: Low, M: Medium, H: High
Overall Status
09 Apr | 16 Apr | 23 Apr | 30 Apr | 07 Mai | 14 Mai | 21 Mai | 28 Mai | 04 Jun | 11 Jun
Week ending
Key Milestones of Release 2021.2 - Sprints
Milestones
SIT
Owner : José
Challenged
Main Issues / Risks | Impact
E2E test milestones are not finalized for release 2021.2, which brings risks for time | H
Requirements started late for release 2021.2, which is delaying estimations and impacting planning | H
Main Achievements
Quality gate passed for all the new code and improved for legacy code
SIT
SIT
SIT
SIT

## Slide 4: UI STREAM – Scope & estimates (High Level)
*Real-World Engineering Days (excluding QA)
Epic | Effort* | UI* | API* | Remarks
Technical debt - Upgrade old Java Packages (XRAY) | 10 | 0 | 10 | 
Time series – Accounts | 35 | 15 | 20 | 
IDMTST - UI Enhancements | 10 | 5 | 5 | 
Xref table updates in Datahub - UI Enhancements – Operations updates | 28 | 14 | 14 | 
UI Enhancements approvals screen x2 / UI Risk Measurements timestamps | 5 | 4 | 1 | 
Technical debt - Data API Upgrade | 15 | 0 | 15 | 
Technical debt - Fund Structure optimization to improve performance | 30 | 20 | 10 | 
Auditing and reporting | 15 | 0 | 15 | 
TOTAL | 148 | 48 | 100 | 

## Slide 5: UI STREAM – pre-requisites (EPICS)
Team | Epic (Team) | Overall | Requirements | UX | User Stories | Refinement | Data Dependencies | Remarks
Orange | Technical debt - Upgrade old Java Packages (XRAY) |  |  |  |  |  |  | 
Orange | Time series – Accounts |  |  |  |  |  |  | 
Orange | IDMTST - UI Enhancements |  |  |  |  |  |  | 
White | Xref table updates in Datahub - UI Enhancements – Operations updates |  |  |  |  |  |  | 
Orange | UI Enhancements approvals screen x2 / UI Risk Measurements timestamps |  |  |  |  |  |  | 
White | Technical debt - Data API Upgrade |  |  |  |  |  |  | 
White | Technical debt - Fund Structure optimization to improve performance |  |  |  |  |  |  | 
White | Auditing and reporting |  |  |  |  |  |  | 
 | Overall |  |  |  |  |  |  | 
Color legend:Completed, On track, Challenged, Blocked, - na

## Slide 6: UI STREAM – Scope & ESTIMATES (breakdown) (1/2)
*Real-World Engineering Days (excluding QA)
Epic | Effort* | Features breakdown | Effort* | Remarks
Technical debt - Upgrade old Java Packages (XRAY) | 10 | Java Package Upgarde | 10 | 
Time series – Accounts | 35 | Add TS Record | 5 | 
 |  | TS AM Approval List | 4 | 
 |  | TS AM Approve Reject | 6 | 
 |  | TS AM Create Account | 5 | 
 |  | TS AM Edit | 4 | 
 |  | TS AM List View | 10 | 
IDMTST - UI Enhancements | 10 | IDMTST | 10 | 
Xref table updates in Datahub | 28 | Amend | 2 | 
 |  | Approve/Reject | 4 | 
 |  | Create | 4 | 
 |  | Edit | 2 | 
 |  | General | 3 | 
 |  | Inactivating | 2 | 
 |  | List View | 4 | 
 |  | Pre-visualiation | 2 | 
 |  | Send for Approval | 3 | 
 |  | View | 2 | 

## Slide 7: UI STREAM – Scope & ESTIMATES (breakdown) (2/2)
*Real-World Engineering Days (excluding QA)
Epic | Effort* | Features breakdown | Effort* | Remarks
UI Enhancements approvals screen x2 / UI Risk Measurements timestamps | 5 | UI Enhancements approvals screen x2 / UI Risk Measurements timestamps | 5 | 
Technical debt - Data API Upgrade | 15 | Data API Upgrade | 15 | 
Technical debt - Fund Structure optimization to improve performance | 30 | Fund Structure optimization to improve performance | 30 | 
Auditing and reporting | 15 |  | 15 | 
Risk: Effort in creased to 30 MD and therefore descoped from the release 2021.1
Risk: We didn’t get any requirement yet for Auditing and reporting

## Slide 8: UI STREAM – Team Capacity
UI Team | Sprint 26 | Sprint 27 | Sprint 28 | Sprint 29
White | 18.2 | 13.2 | 10.0 | 12.7
Orange | 13.7 | 10.9 | 11.4 | 8.6
TOTAL | 31.9 | 24.1 | 21.4 | 21.4
Baseline Capacity – incl. Vacations and Holidays
Team 2 - White
Team 1 –Orange
Remarks
We have stabilized the two teams by balancing the capacity in both teams according the new organisation
Sudhakar | G | SM | Chennai
Deepa | Elumalai | BA | Chennai
David | Duret | BA | Paris
Kumaresan | Jayaraman | FS DEV | Chennai
Ramesh | Ulaganathan | FS DEV | Chennai
Ramesh | ARUMUGAM | UI DEV | Chennai
Ariharasubashini | S | FS DEV | Chennai
Manish | JHA | FS DEV | Paris
Saravanan | Meenakshisundaram | QA | Chennai
Senthil | NARAYANASAMY | QA | Chennai
Guylaine | Schorter | SM | Paris
Catherine | Allix | BA | Paris
Jean-Marie | Gagnaire | FS DEV | Paris
Haripriya | PS | FS DEV | Chennai
Lahcen | Elalem | API DEV | Paris
Mariyappan | MUTHABISHEGAM | API DEV | Chennai
Zied | ECHEIKH | FS DEV | Paris
Xavier | Auberon | QA | Paris
Ramana | CHANDAR | QA | Chennai
The capacity shown here (MD) is for new features development only (excl. time for non-engineering tasks, bug fixing, production support and unplanned tasks)
 | effort | capacity | diff
UI | 48 | 60 | 12
API | 100 | 59 | -41
TOTAL | 148 | 119 | -29
Capacity Check
Risk: The required capacity is not secured. In particular, on the API developers side

## Slide 9: UI STREAM - Timeline
Risk: We are still doing Bug fixing that is supposed to be finished during the stabilization phase of the 21.1 release that is impacting the planning for 21.2 release
Preparing R2021.2
Production Incidents (5%)
Bug fixing (30%)
Month
4
14
Week ending
Features
Sprints
PROD
Apr
Mai
stabilization
Juin
7
30
21
16
23
L3 support
Xref table updates in Datahub
QA
Refinements
drop 1
drop 2
drop 4
SIT
R2021.2
drop 3
UAT
Q.G.
Aftercare
R2021.1
Tech. Check Doc
Q.G.
Aftercare
9
Sprint 26
IDMTST
Time Series for Accounts
Sprint 27
Tech. Check Doc
28
11
Upgrade old Java Packages (XRAY)
Auditing and Reporting
Upgrade Data API
FS tactical fix to resolve performance issues
Sprint 28
Sprint 29
Preparing R2021.3
UI Enhancements approvals screen

## Slide 10: UI STREAM – progress DASHBOARD
Team | Epic | Epic | Sprint 26 | Sprint 27 | Sprint 28 | Sprint 29 | Pending (#US) | Total (#US) | Remarks
Orange | Technical debt - Upgrade old Java Packages (XRAY) |  | Xray upgrade |  |  |  | 1 | 1 | 
Orange | Time series – Accounts |  | Add TS Record, TS AM Create Account, TS AM Approval List | TS AM Approve Reject, TS AM Edit, Add TS Record | TS AM Approve Reject,TS AM List View |  | 4 | 15 | 
Orange | IDMTST - UI Enhancements |  |  |  | IDMTST-994, IDMTST-1415, IDMTST-1060, IDMTST-1182 | IDMTST-565, IDMTST-1085, IDMTST-1058 | 0 | 7 | 
White | Xref table updates in Datahub - UI Enhancements – Operations updates |  | Create, Approve/Reject, Pre-visualization | Amend, General, List View, Send for Approval, View, Inactivating, Edit |  |  | 8 | 25 | 
Orange | UI Enhancements approvals screen x2 / UI Risk Measurements timestamps |  |  |  | UI Enhancements approvals |  | - | - | 
White | Technical debt - Data API Upgrade |  |  |  | Data API Upgrade |  | 1 | 1 | 
White | Technical debt - Fund Structure optimization to improve performance |  |  |  |  | Fund Structure optimization | 1 | 1 | 
White | Auditing and reporting |  |  |  |  | Auditing and reporting(*) | - | - | 
Features are shown on their ending sprint
Color legend:Completed, On track, Challenged, Blocked, - NA
Risk: Requirement are not available yet for Auditing and reporting
Risk: To be checked for the requirement

## Slide 11: UI Team – Productivity (orange & white)

## Slide 12: UI Team – Release Burndown (orange & white)

## Slide 13: UI Team - Bugs fixing (all & high )
All severity levels
High-severity only (i.e. blocker and critical)

## Slide 14: UI Team - Code Quality (UI & API)
Risk: Legacy code coverage and code smells will be addressed as part of technical debt in a future release

## Slide 15: UI STREAM – Issues & Risks
L: Low, M: Medium, H: High
Issues and Risks | Impact | Likely | Mitigation Plan
E2E test milestones are not finalized for release 2021.1, which brings risks for time | H | 100% | Escalated
Requirements started late for release 2021.2, which is delaying estimations and impacting planning | H | 100% | Escalated

## Slide 16: UI Stream – Deployments
Version | IST Date (EOD) | UAT Date (10am CET) | Remarks
0.11.18 | 09-Apr | 10-Apr | Drop 13 of release 2021.1

## Slide 17: Thank You